## Goal Tracker
Month | Activity | Goal | Consultant | Hours | Goal(s) | July | August | September | ∑
July | 3.3.6 | 3 | Ted Burke | 1 | 1 | 48 | 19.5 | 80 | 147.5
July | 3.5.5 | 3 | Ted Burke | 4 | 2 | 65 | 99 | 170.5 | 334.5
July | 5.4.1 | 5 | Ted Burke | 1.5 | 3 | 75.667 | 147.5 | 316.5 | 539.667
July | 3.5.5 | 3 | Ted Burke | 4.5 | 4 | 60.5 | 1 | 19.5 | 81
July | 5.4.1 | 5 | Ted Burke | 4 | 5 | 195 | 57 | 94.5 | 346.5
July | 3.3.6 | 3 | Ted Burke | 1 | a | 2 | 0 | 4 | 6
July | 3.5.5 | 3 | Ted Burke | 9.5 | o | 18.5 | 10.5 | 16 | 45
July | 5.4.1 | 5 | Ted Burke | 1.5 | Total | 464.667 | 334.5 | 701 | 1500.167
July | 3.3.6 | 3 | Ted Burke | 1
July | 3.5.5 | 3 | Ted Burke | 3 | Month | Total
July | 5.1.4 | 5 | Ted Burke | 4.5 | July | 464.667
July | 5.2.5 | 5 | Ted Burke | 22 | August | 334.5
July | 1.5. | 1 | Linda Goodman | 8 | September | 701
July | 2.3.2.3 | 2 | Linda Goodman | 6 | Total | 1500.167
July | 5.4.1 | 5 | Linda Goodman | 2
July | 2.3.2.3 | 2 | Linda Goodman | 9.5
July | 5.4.1 | 5 | Linda Goodman | 1.5
July | other | o | Linda Goodman | 5
July | 1.5.1 | 1 | Linda Goodman | 5
July | 2.3.2.3 | 2 | Linda Goodman | 3
July | 2.4.1 | 2 | Linda Goodman | 6.5
July | 5.4.1 | 5 | Linda Goodman | 0.5
July | other | o | Linda Goodman | 5.5
July | 1.5.1 | 1 | Linda Goodman | 13.5
July | 2.3.2.3 | 2 | Linda Goodman | 7
July | 2.3.2.3 | 2 | Linda Goodman | 6
July | 4.1.4 | 4 | Darla Gundler | 6
July | 5.1.4 | 5 | Darla Gundler | 6
July | 5.2.4 | 5 | Darla Gundler | 12
July | 5.4.1 | 5 | Darla Gundler | 8
July | admin | a | Darla Gundler | 2
July | 2.5. | 2 | Darla Gundler | 3
July | 4.1.8 | 4 | Darla Gundler | 31
July | 5.1.5 | 5 | Darla Gundler | 2
July | other | o | Darla Gundler | 4
July | 2.4. | 2 | Darla Gundler | 2
July | 3.4.6 | 3 | Darla Gundler | 5
July | 4.1.4 | 4 | Darla Gundler | 9
July | 4.4.4 | 4 | Darla Gundler | 2
July | 5.1.4 | 5 | Darla Gundler | 8
July | 5.1.5 | 5 | Darla Gundler | 4
July | 5.2.1 | 5 | Darla Gundler | 4
July | 5.4.1 | 5 | Darla Gundler | 2
July | other | o | Darla Gundler | 4
July | 3.3.5 | 3 | Darla Gundler | 2
July | 4.1.4 | 4 | Darla Gundler | 4
July | 5.1.4 | 5 | Darla Gundler | 2
July | 5.1.5 | 5 | Darla Gundler | 2
July | 5.2.5 | 5 | Darla Gundler | 30
July | 2.4.1 | 2 | Darla Gundler | 5
July | 2.4.3 | 2 | Darla Gundler | 2
July | 2.4.4 | 2 | Darla Gundler | 1
July | 2.5. | 2 | Darla Gundler | 5
July | 3.3.3 | 3 | Darla Gundler | 12
July | 3.3.5 | 3 | Darla Gundler | 7
July | 5.1.6 | 5 | Darla Gundler | 2
July | 5.4.1 | 5 | Darla Gundler | 6
July | 3.5.2 | 3 | Susan Maude | 0.5
July | 3.5.4 | 3 | Susan Maude | 6
July | 3.5.5 | 3 | Susan Maude | 0.5
July | 2.4.1.1 | 2 | Susan Maude | 2
July | 3.5.2 | 3 | Susan Maude | 2
July | 3.5.5 | 3 | Susan Maude | 2
July | 2.4.1.1 | 2 | Susan Maude | 1
July | 3.5.4 | 3 | Susan Maude | 0.5
July | 3.5.5 | 3 | Susan Maude | 0.5
July | 3.5.2 | 3 | Susan Maude | 0.167
July | 3.5.4 | 3 | Susan Maude | 3
July | 5.4. | 5 | Susan Maude | 2
July | 2.4.1.1 | 2 | Susan Maude | 3
July | 3.2. | 3 | Deborah Rooks- Ellis | 3
July | 5.2.4 | 5 | Deborah Rooks- Ellis | 5
July | 5.1.4 | 5 | Deborah Rooks- Ellis | 5
July | 5.2.4 | 5 | Deborah Rooks- Ellis | 19
July | 5.1.4 | 5 | Jennifer Amilivia | 5
July | 5.2.4 | 5 | Jennifer Amilivia | 18
July | 3.2.2 | 3 | Vicki Stayton | 1
July | 5.4.1 | 5 | Vicki Stayton | 4
July | 1.3. | 1 | Vicki Stayton | 2.5
July | 2.2.2.1 | 2 | Vicki Stayton | 2
July | 3.2.2 | 3 | Vicki Stayton | 1
July | 5.4.1 | 5 | Vicki Stayton | 1.5
July | 1.3. | 1 | Vicki Stayton | 17
July | 1.3.3 | 1 | Vicki Stayton | 2
July | 3.2.2 | 3 | Vicki Stayton | 1
July | 4.1.4 | 4 | Vicki Stayton | 6
July | 5.1.4 | 5 | Vicki Stayton | 5.5
July | 2.2.2.1 | 2 | Vicki Stayton | 1
July | 3.2.2 | 3 | Vicki Stayton | 3.5
July | 4.1. | 4 | Vicki Stayton | 2.5
July | 5.2.5 | 5 | Vicki Stayton | 1
July | 5.4.1 | 5 | Vicki Stayton | 1
July | 3.3.3 | 3 | Vicki Stayton | 1
July | 5.4.1 | 5 | Vicki Stayton | 2.5
August | 2.3. | 2 | Deborah Rooks- Ellis | 7.5
August | 3.5. | 3 | Deborah Rooks- Ellis | 28.5
August | 5 | 5 | Deborah Rooks- Ellis | 5
August | 2.3. | 2 | Deborah Rooks- Ellis | 8
August | 2.3. | 2 | Deborah Rooks- Ellis | 3
August | 5.1.7 | 5 | Jennifer Amilivia | 2
August | 5.4.1 | 5 | Jennifer Amilivia | 2
August | 5.1.7 | 5 | Jennifer Amilivia | 2
August | 5.4.1 | 5 | Jennifer Amilivia | 8
August | 2.3.2 | 2 | Jennifer Amilivia | 22
August | 5.1.7 | 5 | Jennifer Amilivia | 1
August | 5.4.1 | 5 | Jennifer Amilivia | 1
August | 2.3.2 | 2 | Jennifer Amilivia | 8
August | 5.1.7 | 5 | Jennifer Amilivia | 1
August | 5.4.1 | 5 | Jennifer Amilivia | 2
August | 5.4.1 | 5 | Jennifer Amilivia | 2
August | 1.5.1 | 1 | Linda Goodman | 1
August | 2.3.2.3 | 2 | Linda Goodman | 4
August | other | o | Linda Goodman | 3
August | 2.4.1.1 | 2 | Linda Goodman | 11.5
August | 5.1.5 | 5 | Linda Goodman | 1
August | 5.4.1 | 5 | Linda Goodman | 1
August | other | o | Linda Goodman | 2.5
August | 2.3.2.3 | 2 | Linda Goodman | 1
August | 2.4.1.1 | 2 | Linda Goodman | 13
August | other | o | Linda Goodman | 2
August | 3.5.5 | 3 | Linda Goodman | 23
August | 5.1.5 | 5 | Linda Goodman | 3.5
August | 2.3.2.3 | 2 | Linda Goodman | 4
August | 2.4.1.1 | 2 | Linda Goodman | 1
August | other | o | Linda Goodman | 3
August | 2.4.1.1 | 2 | Susan Maude | 2
August | 3.5.5 | 3 | Susan Maude | 3
August | 3.5.7.4 | 3 | Susan Maude | 2
August | 5.4.1 | 5 | Susan Maude | 1
August | 3.5.7 | 3 | Susan Maude | 4.5
August | 5.4.1 | 5 | Susan Maude | 2
August | 3.5.5 | 3 | Susan Maude | 36
August | 3.5.6 | 3 | Susan Maude | 1
August | 3.5.1 | 3 | Susan Maude | 0.5
August | 2.3.2 | 2 | Ted Burke | 2
August | 3.4.7 | 3 | Ted Burke | 2
August | 3.5.5 | 3 | Ted Burke | 2
August | 5.4.1 | 5 | Ted Burke | 1.5
August | 2.3.2 | 2 | Ted Burke | 1.5
August | 3.5.5 | 3 | Ted Burke | 4
August | 5.4.1 | 5 | Ted Burke | 1.5
August | 3.3.4 | 3 | Ted Burke | 2
August | 3.4.7 | 3 | Ted Burke | 4
August | 3.5.5 | 3 | Ted Burke | 2
August | 5.4.1 | 5 | Ted Burke | 1.5
August | 3.4.7 | 3 | Ted Burke | 28
August | 5.1.7 | 5 | Ted Burke | 5
August | 5.4. | 5 | Ted Burke | 1.5
August | 3.5.5 | 3 | Ted Burke | 5
August | 5.4.1 | 5 | Ted Burke | 1.5
August | 1.3.3 | 1 | Vicki Stayton | 4
August | 2.3.2.1 | 2 | Vicki Stayton | 1.5
August | 5.2.1 | 5 | Vicki Stayton | 1
August | 5.4.1 | 5 | Vicki Stayton | 1.5
August | 1.3. | 1 | Vicki Stayton | 3
August | 1.3.3 | 1 | Vicki Stayton | 2.5
August | 2.2.2.1 | 2 | Vicki Stayton | 1
August | 2.3.2 | 2 | Vicki Stayton | 3
August | 2.3.2.1 | 2 | Vicki Stayton | 1
August | 4.1. | 4 | Vicki Stayton | 1
August | 5.4.1 | 5 | Vicki Stayton | 1
August | 2.3.2 | 2 | Vicki Stayton | 4
August | 5.1.4 | 5 | Vicki Stayton | 3
August | 1.3. | 1 | Vicki Stayton | 9
August | 5.4.1 | 5 | Vicki Stayton | 3.5
September | 2.4.4 | 2 | Darla Gundler | 2
September | 3.3.1 | 3 | Darla Gundler | 5
September | 3.3.3 | 3 | Darla Gundler | 2
September | 3.3.5 | 3 | Darla Gundler | 4
September | 3.4.6 | 3 | Darla Gundler | 7
September | 3.5. | 3 | Darla Gundler | 2
September | 3.5.7 | 3 | Darla Gundler | 2
September | 5.2.4 | 5 | Darla Gundler | 4
September | admin | a | Darla Gundler | 4
September | 2.4.1 | 2 | Darla Gundler | 20
September | 3.3.5 | 3 | Darla Gundler | 16
September | 4.1. | 4 | Darla Gundler | 4
September | 3.5.5 | 3 | Darla Gundler | 4
September | 4.1. | 4 | Darla Gundler | 4
September | 4.1.4 | 4 | Darla Gundler | 2
September | 4.1.8 | 4 | Darla Gundler | 6
September | 4.2. | 4 | Darla Gundler | 2
September | 5.1.5 | 5 | Darla Gundler | 2
September | 5.1.8 | 5 | Darla Gundler | 8
September | 5.2.1 | 5 | Darla Gundler | 2
September | 5.4.1 | 5 | Darla Gundler | 6
September | other | o | Darla Gundler | 4
September | 3.3.3 | 3 | Darla Gundler | 35
September | 3.5.5 | 3 | Darla Gundler | 4
September | 5.2.1 | 5 | Darla Gundler | 1
September | 1.4. | 1 | Deborah Rooks- Ellis | 16
September | 1.4. | 1 | Deborah Rooks- Ellis | 12
September | 2.3. | 2 | Deborah Rooks- Ellis | 4
September | 2.3.2 | 2 | Deborah Rooks- Ellis | 5
September | 2.3.2.4 | 2 | Deborah Rooks- Ellis | 2
September | 2.3.4 | 2 | Deborah Rooks- Ellis | 2
September | 3.2.4 | 3 | Deborah Rooks- Ellis | 24
September | 1.4. | 1 | Deborah Rooks- Ellis | 8
September | 2.3.2.4 | 2 | Deborah Rooks- Ellis | 8
September | 3.5. | 3 | Deborah Rooks- Ellis | 1
September | 1.4. | 1 | Deborah Rooks- Ellis | 10
September | 2.3.2 | 2 | Deborah Rooks- Ellis | 13
September | 2.3.2.4 | 2 | Deborah Rooks- Ellis | 8
September | 5.4.1 | 5 | Deborah Rooks- Ellis | 9
September | 2.3. | 2 | Deborah Rooks- Ellis | 6
September | 2.3.2 | 2 | Deborah Rooks- Ellis | 6
September | 2.3.2.4 | 2 | Deborah Rooks- Ellis | 2
September | 2.3. | 2 | Jennifer Amilivia | 2
September | 3.3. | 3 | Jennifer Amilivia | 24
September | 5.4.1 | 5 | Jennifer Amilivia | 6
September | 3.3.4 | 3 | Jennifer Amilivia | 26
September | 5.1.7 | 5 | Jennifer Amilivia | 2
September | 5.4.1 | 5 | Jennifer Amilivia | 18
September | 2.3.2 | 2 | Jennifer Amilivia | 33
September | 5.1.7 | 5 | Jennifer Amilivia | 3
September | 5.4.1 | 5 | Jennifer Amilivia | 4
September | 3.3.4 | 3 | Jennifer Amilivia | 5
September | 2.3. | 2 | Jennifer Amilivia | 4
September | 5.4.1 | 5 | Jennifer Amilivia | 2
September | 1.5.1 | 1 | Linda Goodman | 2
September | 2.4.1.1 | 2 | Linda Goodman | 6
September | 5.4.1 | 5 | Linda Goodman | 3.5
September | other | o | Linda Goodman | 4.5
September | 1.5.1 | 1 | Linda Goodman | 18
September | 2.3. | 2 | Linda Goodman | 4
September | 5.4.1 | 5 | Linda Goodman | 1
September | 1.5.1 | 1 | Linda Goodman | 2
September | 2.3.2.3 | 2 | Linda Goodman | 6
September | 3.5. | 3 | Linda Goodman | 0.5
September | 3.5.5 | 3 | Linda Goodman | 1
September | other | o | Linda Goodman | 6.5
September | 2.3.2.3 | 2 | Linda Goodman | 8
September | 2.4.1 | 2 | Linda Goodman | 3
September | 3.5.5 | 3 | Linda Goodman | 1
September | 5.1.5 | 5 | Linda Goodman | 1
September | 5.4.1 | 5 | Linda Goodman | 2
September | other | o | Linda Goodman | 1
September | 3.3. | 3 | Maureen Greer | 24
September | 3.5.5 | 3 | Susan Maude | 1
September | 3.5.7.3 | 3 | Susan Maude | 1
September | 5.4.1 | 5 | Susan Maude | 1
September | 3.5.7.4 | 3 | Susan Maude | 6
September | 3.5.6 | 3 | Susan Maude | 4
September | 3.5.6 | 3 | Susan Maude | 16
September | 5.4.1 | 5 | Susan Maude | 4
September | 3.5.5 | 3 | Ted Burke | 13.5
September | 5.4.1 | 5 | Ted Burke | 2.5
September | 3.5.5 | 3 | Ted Burke | 11
September | 5.4.1 | 5 | Ted Burke | 3.5
September | 3.5.5 | 3 | Ted Burke | 24.5
September | 5.4.1 | 5 | Ted Burke | 1.5
September | 3.5.5 | 3 | Ted Burke | 6
September | 5.4.1 | 5 | Ted Burke | 1.5
September | 3.2.2 | 3 | Ted Burke | 2
September | 3.5.5 | 3 | Ted Burke | 2
September | 5.2.1 | 5 | Vicki Stayton | 2
September | 1.3. | 1 | Vicki Stayton | 1
September | 2.3.2 | 2 | Vicki Stayton | 5.5
September | 3.3. | 3 | Vicki Stayton | 21
September | 1.3. | 1 | Vicki Stayton | 3
September | 2.3.2 | 2 | Vicki Stayton | 13
September | 3.2. | 3 | Vicki Stayton | 2.5
September | 3.2.4 | 3 | Vicki Stayton | 1
September | 3.3.3 | 3 | Vicki Stayton | 2.5
September | 4.1. | 4 | Vicki Stayton | 1
September | 4.1.4 | 4 | Vicki Stayton | 0.5
September | 5.4.1 | 5 | Vicki Stayton | 0.5
September | 1.3. | 1 | Vicki Stayton | 6
September | 2.3.2 | 2 | Vicki Stayton | 4
September | 2.3.2.1 | 2 | Vicki Stayton | 4
September | 3.2.2 | 3 | Vicki Stayton | 3.5
September | 3.3.3 | 3 | Vicki Stayton | 9.5
September | 5.2.1 | 5 | Vicki Stayton | 1.5
September | 5.2.2 | 5 | Vicki Stayton | 2
September | 1.3. | 1 | Vicki Stayton | 2
September | 3.2.2 | 3 | Vicki Stayton | 2
Note on B98: Joachim,Woodlyn: check with Betsey to confirm activity level.
The number of hours worked is listed by goal and month.
"a"= admin
"o"= Other

## Consultant Trancker
Sum of Hours per Goal | Goals
Consultants | 1 | 2 | 3 | 4 | 5 | a | o | Total Hours
Darla Gundler |  | 40 | 107 | 70 | 111 | 6 | 12 | 346
Deborah Rooks- Ellis | 46 | 74.5 | 56.5 |  | 43 |  |  | 220
Jennifer Amilivia |  | 69 | 55 |  | 79 |  |  | 203
Linda Goodman | 49.5 | 99.5 | 25.5 |  | 17 |  | 33 | 224.5
Maureen Greer |  |  | 24 |  |  |  |  | 24
Susan Maude |  | 8 | 90.167 |  | 10 |  |  | 108.167
Ted Burke |  | 3.5 | 132 |  | 55 |  |  | 190.5
Vicki Stayton | 52 | 40 | 49.5 | 11 | 31.5 |  |  | 184
Total Hours | 147.5 | 334.5 | 539.667 | 81 | 346.5 | 6 | 45 | 1500.167
46+
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Use the slicers (to your left) to filter for desired month, goal, or activity. The number of hours worked will appear next to the name of each consultant on the table and at the botom of the graph below.
"a"= admin
"o"= Other